## Sheet1
Madison Electric Works Chapter 324 Level 4 Interconnection Queue
***Project details included in this Interconnections table reflect Level 4 applications under the MPUC Chapter 324 Rule as of August 2018 only. Generation requests and generators interconnected to the CMP network prior to 2018 (whether under MPUC Chapter 324 or previous interconnection procedures) are not captured in this table.*** | [10 empty] | Feasibility Study |  | Impact Study |  | Combined Study |  | ReStudy |  | Facility Study
PRJ | Queue Position | Dependency (D) | Date App Rec'd | Town | Substation | Circuit | Type of Generation | Total Size (kW) | Total Size (MW) | Battery Size (kW) | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Start | Completion | Fully Executed Interconnection Agreement | Estimated Commercial Operation Date | Status | 115 kV SS | T. Level 0=Screen NC=Non-Comp 3=Full | i39: RC Approval S = Submitted A = Approved | STATUS | GFOV Determination
1 | 1 | 0 | 2020-04-07 | Madsion | Anson | 34.5 | Solar |  | 20 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55 | 1 - HORD
56 | 2 - HORD
57
58 | 3 - HORD
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87 | 1 - BNHE
88
89
90
91 | 1 - BONE
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130 | 1 - BALD
131
132
133
134
135 | 1 - MONM
136 | 2 - MONM
137 | 2 - MONM
138
139
140 | 1 - GUIL
141
142
143
144
145
146
147
148
149
150
151
152 | 1 - LEED
153
154
155
156
157
158 | 1 - STUR
159
160 | 1 - NEWP
161
162
163
164
165 | 4 - MONM
166
167
168
169 | 1 - CARM
170
171
172
173
174
175
176
177 | 2 - CARM
178
179
180
181
182
183
184 | 1 - SKTP
185 | 2 - SKTP
186
187
188 | 1 - BR34
189
190
191
192
193
194
195
196
197
198
199
200 | 2 - LEED
201
202
203
204 | 2 - STUR
205 | 1 - UNIT
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230 | 2 - GUIL
231
232
233
234 | 1 - LOVE
235
236
237
238
239
240
241 | 1 - WINS
242 | 2 - WINS
243 | 3 - WINS
244
245
246
247
248
249 | 1 - SKNS
250
251
252
253
254
255 | 1 - FOHI
256
257
258
259
260
261
262 | 0
263 | 5 - MONM
264
265 | 1 - OAKL
266
267 | 6 - MONM
268
269
270
271
272
273
274
275
276
277
278
279 | 2 - UNIT
280
281 | 1 - VASS
282
283
284 | 4 - HORD
285
286 | 4 - WINS
287 | 1 - NORW
288 | 2 - SKNS
289 | 3 - SKNS
290
291
292
293
294
295
296
297
298
299 | 5 - HORD
300
301
302
303 | 3 - STUR
304 | 4 - STUR
305
306 | 1 - CORI
307 | 1 - LVFA
308 | 1 - DEXT
309 | 2 - DEXT
310 | 1 - WINT
311
312
313
314
315 | 0
316
317 | 2 - NORW
318
319
320
321
322 | 3 - SKTP
323
324
325
326
327
328
329 | 1 - DEER
330
331
332
333
334 | 2 - VASS
335 | 4 - SKTP
336
337
338
339
340 | 5 - STUR
341 | 1 - NOLI
342 | 1 - WATE
343
344
345
346 | 3 - VASS
347
348
349
350 | 1 - MANC
351 | 1 - NOAU
352 | 1 - COMR
353
354
355
356 | 6 - STUR
357
358
359
360
361
362 | 2 - WATE
363 | 2 - COMR
364 | 2 - BONE
365
366
367
368 | 1 - BEWE
369 | 2 - BEWE
370 | 1 - MEFA
371 | 4 - VASS
372
373 | 2 - LVFA
374
375 | 2 - BNHE
376
377
378
379
380
381 | 3 - BEWE
382
383
384 | 1 - BUCO
385 | 1 - GRAY
386
387 | 2 - NOAU
388
389 | 1 - PDRD
390
391
392
393 | 4 - BEWE
394
395
396 | 5 - BEWE
397 | 6 - BEWE
398 | 7 - BEWE
399
400
401
402 | 6 - HORD
403
404 | 2 - DEER
405
406
407 | 1 - RRPS
408
409
410 | 2 - LOVE
411
412 | 1 - DOVE
413
414
415
416
417 | 0
418 | 1 - BOND
419
420
421
422
423
424
425
426
427
428
429
430 | 1 - BROO
431
432 | 7 - STUR
433 | 2 - BROO
434 | 3 - NOAU
435
436
437
438
439
440 | 1 - NATP
441 | 3 - DEER
442 | 4 - DEER
443 | 2 - GRAY
444
445 | 1 - OXFO
446
447
448
449
450
451 | 1 - LEBA
452
453
454
455
456
457
458
459
460 | 2 - DOVE
461 | 1 - WILT
462 | 4 - NOAU
463 | 8 - STUR
464
465 | 1 - PAPO
466
467 | 1 - WSST
468 | 1 - RILE
469
470 | 1 - ATHN
471 | 1 - THCR
472 | 2 - RRPS
473
474
475
476
477
478
479
480
481 | 3 - RRPS
482 | 2 - WILT
483
484
485
486
487 | 1 - SKSS
488 | 1 - PAST
489 | 1 - SHAW
490
491
492 | 1 - LIME
493 | 1 - BRCR
494
495 | 1 - PROS
496 | 3 - BROO
497
498 | 3 - GUIL
499
500 | 9 - STUR
501
502 | 10 - STUR
503 | 7 - HORD
504 | 1 - TPCO
505
506
507
508
509 | 1 - PATP
510 | 11 - STUR
511 | 1 - BRIS
512 | 3 - DOVE
513 | 1 - BRML
514 | 3 - BNHE
515
516 | 2 - PROS
517
518 | 1 - FRYT
519
520 | 3 - NORW
521 | 2 - NEWP
522 | 2 - LIME
523
524 | 1 - BDPP
525 | 3 - LEED
526 | 1 - MONS
527 | 2 - SHAW
528
529 | 8 - HORD
530 | 5 - NOAU
531 | 1 - BRPO
532
533 | 1 - BDIP
534 | 1 - WYHY
535 | 3 - BONE
536 | 3 - NEWP
537 | 1 - FRYE
538 | 1 - GRFA
539 | 2 - MONS
540 | 1 - LULA
541 | 1 - SAIP
542 | 1 - EMDE
543 | 1 - YOBE
544
545 | 4 - DOVE
546 | 1 - CAMD
547 | 1 - TPOL
548 | 1 - MCCO
549 | 1 - SOWA
550 | 2 - SAIP
551 | 2 - LEBA
552 | 1 - WARR
553 | 3 - CARM
554 | 1 - FREE
555 | 2 - PAST
556 | 1 - WSTN
557 | 1 - MERO
558 | 1 - LSFA
559
560 | 1 - R115
561 | 1 - AGK5
562 | 1 - LISB
563
564 | 3 - COMR
565 | 1 - SWRD
566
567 | 1 - HIST
568 | 1 - SOBE
569
570 | 1 - PHST
571 | 2 - PHST
572 | 3 - MONS
573 | 8 - BEWE
574 | 1 - DETR
575 | 1 - FAFA
576 | 1 - RUMF
577 | 4 - RRPS
578 | 2 - SWRD
579 | 1 - WEBR
580 | 2 - EMDE
581 | 2 - RILE
582 | 1 - PLHL
583 | 1 - ELIO
584 | 2 - BALD
585
586 | 1 - SMRD
587 | 4 - LEED
588 | 1 - BASS
589 | 4 - GUIL
590 | 4 - CARM
591 | 2 - ELIO
592 | 1 - FAIR
593
594 | 1 - MAST
595
596 | 1 - HITP
597 | 3 - LVFA
598 | 6 - NOAU
599 | 1 - CH12
600 | 1 - PRCO
601 | 2 - FREE
602 | 1 - ANDO
603 | 1 - SHEE
604 | 2 - MEFA
605 | 1 - EWIL
606 | 2 - RUMF
607 | 2 - WINT
608 | 1 - MESS
609 | 1 - WALD
610 | 2 - FOHI
611 | 5 - DEER
612 | 12 - STUR
613 | 1 - PRAT
614 | 3 - PAST
615
616
617 | 1 - LINC
618 | 2 - DETR
619 | 2 - PRCO
620 | 3 - PRCO
621 | 1 - NWVI
622 | 1 - MARO
623 | 4 - LVFA
624 | 1 - HIHY
625 | 9 - BEWE
626 | 1 - DUNS
627 | 1 - CONY
628 | 2 - THCR
629 | 1 - BRID
630 | 1 - BATH
631 | 2 - DUNS
632 | 1 - ANSO
633 | 1 - SASW
634
635 | 3 - PHST
636 | 4 - PRCO
637 | 1 - CAEL
638 | 4 - NEWP
639 | 1 - NOWI
640 | 2 - LSFA
641 | 1 - SEAR
642 | 1 - DAMS
643 | 3 - LSFA
644 | 2 - BATH
645 | 0
646 | 2 - SKSS
647 | 13 - STUR
648 | 2 - MANC
649 | 1 - SABA
650 | 2 - PAPO
651 | 1 - KITT
652 | 1 - BUCK
653 | 3 - WINT
654 | 3 - RUMF
655 | 2 - BUCK
656 | 2 - R115
657 | 3 - DEXT
658 | 2 - SOBE
659 | 7 - MONM
660 | 1 - COCO
661 | 5 - GUIL
662 | 1 - BANE
663 | 3 - SKSS
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
0
0